P032 - Garden Fleet 01 Schedule



Schedule

* 1. Organisation Overview
		1. Phase 1- Port
			+ Legal Setup
			+ Token IEO
			+ Port Buildout (Palawan)
		2. Phase 2 - Fleet
			+ Fleet Deployment
			+ Initial Cleanup
			+ Initial Reforestation
		3. Phase 3 - Community
			+ Community Integration
			+ Dashboard Launch
			+ Service Expansion
		4. Phase 4 (2027): Government ESG contract
			+ Contract 1
				- Onboarding
				- Auditing
			+ Contract 2
				- Onboarding
				- Auditing
			+ Contract 3
				- Onboarding
				- Auditing
		5. Phase 5 (2028–2029): Regional scaling
			+ Port 2 Established
			+ Port 3 Established
			+ Port 4 Established
	2. Operational Overview
		1. Plastic Recycling Project
			+ Setup & Planning (May–June 2025)
				- Land acquisition (3000–5000 sq ft)
				- Permitting and licensing
				- Machinery procurement and vendor agreements
				- Staff recruitment and training
			+ Collection & Warehousing (July 2025 onward)
				- Deploy bins (50–100 public locations)
				- Launch community awareness drives
				- Activate mobile collection vans
				- Hire and deploy 4–6 field staff
			+ Sorting & Storage (July 2025 onward)
				- Set up covered sorting area with color-coded tables
				- Manual/semi-automated sorting (PET, HDPE, LDPE, etc.)
				- Implement daily hygiene, fire, and pest control protocols
			+ Recycling & Manufacturing (August 2025 onward)
				- Install and operate shredders, washers, dryers, moulders
				- Produce recycled pellets, bricks, planters, buckets
				- Quality control and packaging setup
			+ Marketing & Sales (August 2025 onward)
				- Launch online store (Instagram, Facebook, WhatsApp)
				- Build partnerships with eco-stores and construction companies
				- Run 'Trash to Treasure' awareness campaigns
				- Implement Return & Recycle programs and loyalty discounts
		2. Milestone Events
			+ Project Launch (May 2025)
			+ Bin Network Deployment (July 2025)
			+ First 10 Tons Processed (by September 2025)
			+ First Product Launch and Sale (October 2025)
			+ Financial Review and Adjustment (November 2025)